## Requirements (2)
SNo |  | Requirement | Assignee | Efforts | Due Dates | Status | Remarks | Revised
1 | 2024-01-20 | PO Print - color & size needs to be captured | Sunanda | 24 |  | Ready for UAT |  | 25/01/2024 : 7.00PM UAT confirmation : 25/01/2024
2 | 2024-01-20 | HSN code is not required during fabric code creation but it's a mandatory option to be provided during PO creation. Please revise the options as per it. | Manisha | 10 |  | Ready for UAT |  | 25/01/2024 : 7.00PM UAT confirmation : 25/01/2024
3 | 2024-01-20 | In the Fabric / trim code filter option, If the code is available with the parameters entered, the user will select the code from the list If the code is not available, the user will click on a request button where the required parameters are sent to the Sourcing team. The sourcing team will create the code and the user can use the code in sampling screen. | Manisha | 20 |  | Testing | 25/01/2024 : 7.00PM UAT confirmation : 25/01/2024 29/01/2024 : Will be released to testing by 12.00PM | 25/01/2024 : 7.00PM UAT confirmation : 25/01/2024 29/01/2024 : Will be released to testing by 12.00PM
4 | 2024-01-20 | In the Fabric / trim code filter option, If the code is available with the parameters entered, the user will select the code from the list If the code is not available, the user will click on a request button where the required parameters are sent to the Sourcing team. The sourcing team will create the code and the user can use the code in sampling screen. | Manisha |  |  | Inprogress
5 | 2024-01-20 | The "Fabric Upload" option currently takes only one file in image format(JPEG OR PNG). It has to allow uploading multiple files of pdf, image, Excel formats. And the name should also be changed to Upload Tech Pack. | 16 | 20 | 2024-01-18 | Ready for UAT | 2024-01-25 | UAT Confirmation :25/01/2024
6 | 2024-01-20 | Need an option to upload image files in the fabric and trim tabs of sample development | 16 | 20 | 2024-01-20 | Ready for UAT |  | UAT Confirmation :25/01/2024
7 | 2024-01-20 | When the style is selected, The image file attached against the style should be visible in the Sample development screen. | 8 | 10 | 2024-01-17 | Ready for UAT |  | UAT Confirmation :25/01/2024
8 | 2024-01-20 | The "Technician" and "Conversion" and the "Made-In" Fields should be removed. | 1 | 1 | 2024-01-17 | Ready for UAT |  | UAT Confirmation :25/01/2024
9 | 2024-01-20 | Need to change the currently existing "Type" field as "Category" in sample development form | 6 | 8 | 2024-01-17 | Ready for UAT |  | UAT Confirmation :25/01/2024
10 | 2024-01-20 | Need to add new fields "Sub Type" and "Type" in sample development screen | 16 | 20 | 2024-01-18 | Ready for UAT | Based on the selected "Sub Type" the "Type" field will get auto populated | UAT Confirmation :25/01/2024
11 | 2024-01-20 | The Size and Color fields should be dynamically added fields |  |  | 2024-01-18 | Ready for UAT | Restriction is to be added where maximum number colors can be added at a time | UAT Confirmation :25/01/2024
12 | 2024-01-20 | Po Print - Amount in words | 2 | 4 | 2024-01-18 | Ready for UAT |  | UAT Confirmation :25/01/2024
13 | 2024-01-20 | Sample Development request list screen to sourcing ID (screen permission for fabric and trim sourcing users) | 1 | 1 | 2024-01-18 | Ready for UAT |  | UAT Confirmation :25/01/2024
14 | 2024-01-20 | Shrinkage is not mandatory during code creation. Please remove the mandatory * option. in fabric creation master | 1 | 1 | 2024-01-19 | Ready for UAT |  | UAT Confirmation :25/01/2024
15 | 2024-01-20 | A remark option should be provided for additional comments. in fabric creation master | 1 | 1 | 2024-01-17 | Ready for UAT |  | UAT Confirmation :25/01/2024
16 | 2024-02-07 | Size Masters to be created by the marketing team |  | 2 |  | Open
17 | 2024-02-07 | More sampling locations to be added(Based on where the sampling will take place) |  | 3 |  | Open
18 | 2024-02-07 | 340 should be under the warehouse field |  |  |  | Open | Need Clarity
19 | 2024-02-07 | The description should be fetched from the style management |  | 4 |  | Open
20 | 2024-02-07 | The product field should be mandatory |  | 1 |  | Open
21 | 2024-02-07 | Pattern master name needs to be added |  |  |  | Open | Need Clarity
22 | 2024-02-07 | Sample Development view should display sample indents created against the user ID(Only for Merchant login) |  |  |  | Open | Need Clarity
23 | 2024-02-07 | The Hangtag of all the buyers is to be shared |  |  |  | Open | Need Clarity
24 | 2024-02-07 | The operation tab needs to be added to the sample development screen. |  | 8 |  | Open
25 | 2024-02-07 | Acknowledgment of receiving the stock needs to be added for the sampling team |  | 10 |  | Open | Please provide acknowledgment format if have
26 | 2024-02-07 | The Stock return feature needs to be incorporated after further discussions |  |  |  | Open | Need Clarity
27 | 2024-02-07 | Please find the remaining trim masters that have to be configured into the application attached below. |  | 38 |  | Open | New 7 Params identified while comparing the old list( Buyer,Length,Line,Parts,Ply,Shape,Slider)These are new Masters Efforts included for CR and migration)
28 | 2024-02-07 | The Fabric color field needs to be added to the sampling development screen in the fabric section. The data from this field must be considered for the color field in the PO screen. We will ask the merchants to enter the fabric color in the remarks screen for now. The color mentioned in the remarks screen needs to be captured in the PO till the new field is added. |  | 12 |  | Open

## Sheet2
Sno | Raised date | CR | Efforts | Status | Remarks
1 | 2024-02-07 | Size Masters to be created by the marketing team | 2 | Open
2 | 2024-02-07 | More sampling locations to be added(Based on where the sampling will take place) | 3 | Open
3 | 2024-02-07 | 340 should be under the warehouse field | 4 | Need Clarity | Warehouse field will have a singlevalue(340). Location will have drop down list in sample deveopment
4 | 2024-02-07 | The description should be fetched from the style management | 4 | Open
5 | 2024-02-07 | The product field should be mandatory | 1 | Open
6 | 2024-02-07 | Pattern master name needs to be added | 16 | Need Clarity | As per Vishal Type field coverted to pattern master field
7 | 2024-02-07 | Sample Development view should display sample indents created against the user ID(Only for Merchant login) | 8 | Need Clarity | The sample orders created by the particular user only has to be displayed in the view list
8 | 2024-02-07 | The Hangtag of all the buyers is to be shared |  | Need Clarity
9 | 2024-02-07 | The operation tab needs to be added to the sample development screen. | 8 | Open
10 | 2024-02-07 | Acknowledgment of receiving the stock needs to be added for the sampling team | 10 | Open | Please provide acknowledgment format if have
11 | 2024-02-07 | The Stock return feature needs to be incorporated after further discussions |  | Hold | After all the opertions completed agains the sample order the leftover stock is to be clasified as reusable or to be disposed. Vishal Need to discuss with Prasad garu
12 | 2024-02-07 | Please find the remaining trim masters that have to be configured into the application attached below. | 38 | Open | New 7 Params identified while comparing the old list( Buyer,Length,Line,Parts,Ply,Shape,Slider)These are new Masters Efforts included for CR and migration)
13 | 2024-02-07 | The Fabric color field needs to be added to the sampling development screen in the fabric section. The data from this field must be considered for the color field in the PO screen. We will ask the merchants to enter the fabric color in the remarks screen for now. The color mentioned in the remarks screen needs to be captured in the PO till the new field is added. | 12 | Open
|  | Total | 106 |  | Effortsgiven for CR's which have clarity

## Masters
PCH | Product Masters | Made - In Masters | DMM Masters | Category Masters | Sub - Type Masters | Types | Brand Masters
MNB | ANORAK | Woven | ARANGANATHAN M-UNIT-12-MARKETING | Denim | PR07 - 1st Concept Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
MND | APRON | Knits/Hosery | ARUN VEERAPPAN-UNIT-12-MARKETING | Non-Denim | PR12 - 1st Development Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| BAG |  | ASHOK MANO J-UNIT-12-MARKETING |  | FS02 - 1st Fit Sample-100 | FIT SAMPLE | #REF!
| BELT |  | B ARUNKUMAR-UNIT-12-MARKETING |  | PP02 - 1st PP Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| BERMUDA |  | BALAJI PANDURANGAN-UNIT-12-MARKETING |  | PR02 - 1st Proto Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| BIB |  | CHANDRALEKHA DINESH-UNIT-12-MARKETING |  | ST02 - 1st Size - Set Sample-100 | SIZE - SET SAMPLE | #REF!
| BIKNI |  | CHANDRASHEKHAR G SHASTRI-UNIT-12-MARKETING |  | PR08 - 2nd Concept Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| BIKNI SET |  | CHITHRA DURAI-UNIT-12-MARKETING |  | PR13 - 2nd Development Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| BLANKET |  | ELAMURUGU -UNIT-12-MARKETING |  | FS03 - 2nd Fit Sample-100 | FIT SAMPLE | #REF!
| BLAZER |  | G GANESAN-UNIT-12-MARKETING |  | PP03 - 2nd PP Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| BLOUSE |  | G JEBA GNANA SINGH-UNIT-12-MARKETING |  | PR03 - 2nd Proto Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| BOOTIES |  | GOPALAKRISHNAN GUNASEKARAN-UNIT-12-MARKETING |  | ST03 - 2nd Size - Set Sample-100 | SIZE - SET SAMPLE | #REF!
| BOW |  | I PRAKASH-UNIT-12-MARKETING |  | PR09 - 3rd Concept Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| BOXERS |  | JAGAN RAMALINGAM-UNIT-12-MARKETING |  | PR14 - 3rd Development Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| BRACE OVERALLS |  | JANARDHANA M-UNIT-12-MARKETING |  | FS04 - 3rd Fit Sample-100 | FIT SAMPLE | #REF!
| BRAISSERIE |  | K S NEMIDHARAN-UNIT-12-MARKETING |  | PP04 - 3rd PP Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| BRIEFS |  | KARTHIK RAJENDRAN-UNIT-12-MARKETING |  | PR04 - 3rd Proto Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| CAMISOLE |  | KULANDAIVEL P-UNIT-12-MARKETING |  | PR10 - 4th Concept Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| CAMISOLE |  | M MADHAVAN-UNIT-12-MARKETING |  | PR15 - 4th Development Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| CAP |  | MAHENDRAN -UNIT-12-MARKETING |  | PR05 - 4th Proto Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| CAPE |  | MANIGANDAN -UNIT-12-MARKETING |  | PR16 - Adoption Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| CAPRI |  | MANISH PUROHIT-FARIDABAD 1-INFORMATION TECHNOLOGY |  | AD02 - Advertisement (AD) Sample-100 | Buyer Line Review/Marketing/Photoshoot/Advertisement/Catalogue | #REF!
| CARDIGAN |  | MANOJ KUMAR C-UNIT-12-MARKETING |  | AA00 - Alteration-100 | Alternation/Partial Activity/Repair Request | #REF!
| CARGOS |  | MURALI DURAISAMY-UNIT-12-MARKETING |  | PR23 - Buying Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| CHINOS |  | MURALI S V-UNIT-12-MARKETING |  | AD03 - Catalogue Sample-100 | Buyer Line Review/Marketing/Photoshoot/Advertisement/Catalogue | #REF!
| CLOAK |  | MUTHUKUMAR V-UNIT-12-MARKETING |  | PR06 - Concept Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| COAT |  | NAGENDIRAN AYYANDURAI-UNIT-12-MARKETING |  | FS05 - Costing & Fitting Sample-100 | Fit Sample | #REF!
| CORSET |  | NISCHITA R SHETTY-UNIT-12-MARKETING |  | DE04 - Design Concept Sample-100 | Design Sample/Design Development Sample/Design Presentation Sample/Design Concept Sample | #REF!
| CORSET |  | PRARTHANA BHARGAVA-UNIT-12-MARKETING |  | DE02 - Design Development Sample-100 | Design Sample/Design Development Sample/Design Presentation Sample/Design Concept Sample | #REF!
| COVER UP |  | RAKESH SHARMA-UNIT-12-MARKETING |  | DE03 - Design Presentation Sample-100 | Design Sample/Design Development Sample/Design Presentation Sample/Design Concept Sample | #REF!
| CRAVAT |  | RANJIT KUMAR GAUTAM-FARIDABAD 1-INFORMATION TECHNOLOGY |  | DE01 - Design Sample-100 | Design Sample/Design Development Sample/Design Presentation Sample/Design Concept Sample | #REF!
| CREW |  | RAVINDRANATH TAGORE TIRUMALASETTY-UNIT-12-MARKETING |  | DE05 - Design Selection Sample-100 | Design Sample/Design Development Sample/Design Presentation Sample/Design Concept Sample | #REF!
| CREWNECK |  | SANGEETA RAZDAN-UNIT-12-MARKETING |  | DE06 - Developer Sample-100 | Design Sample/Design Development Sample/Design Presentation Sample/Design Concept Sample | #REF!
| CULOTTES |  | SEEMA SINGH-UNIT-12-DESIGN DEVELOPMENT |  | PR11 - Development Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| DRESS |  | SHANMUGAM KULANDAIVEL-UNIT-12-MARKETING |  | MK03 - Dummy Fit Sample-100 | Internal Mock/Rough Body/Dummy/Trial Fit Sample | #REF!
| FACE MASK |  | SHIVAKUMAR G H-UNIT-12-MARKETING |  | FS01 - Fit Sample-100 | Fit Sample | #REF!
| FASHION CREWNEC |  | SIVAKUMAR K-UNIT-12-MARKETING |  | TS02 - GPT Sample-100 | TE-GPT/Testing/Wear Test Sample | #REF!
| FASHION JEANS |  | SURESHKUMAR -UNIT-12-MARKETING |  | TS04 - Garment Shrinkage Sample-100 | TE-GPT/Testing/Wear Test Sample | #REF!
| FASHION POLO |  | T JEEVAN-UNIT-12-MARKETING |  | PP07 - Gold Seal Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| FASHION SHORTS |  | T MAHENDRAN-UNIT-12-MARKETING |  | MK01 - Internal Mock Sample-100 | Internal Mock/Rough Body/Dummy/Trial Fit Sample | #REF!
| GLOVES |  | VADIVEL MURUGAN A-UNIT-12-MARKETING |  | PR19 - Line Adoption (LA) & Fit Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| GOWN |  | VINESH KRISHNAN P P-UNIT-12-MARKETING |  | PR18 - Line Adoption (LA) Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| HALTER |  |  |  | PR17 - Line Review (LR) Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| HANDKERCHIEF |  |  |  | AD00 - Marketing Sample-100 | Buyer Line Review/Marketing/Photoshoot/Advertisement/Catalogue | #REF!
| HEADBAND |  |  |  | AA01 - Part Mock-25 | Alternation/Partial Activity/Repair Request | #REF!
| HENLEY |  |  |  | AA03 - Part Mock-Collar-20 | Alternation/Partial Activity/Repair Request | #REF!
| HIPSTER |  |  |  | AA02 - Part Mock-Collar & Collar band-25 | Alternation/Partial Activity/Repair Request | #REF!
| HOODY |  |  |  | AA05 - Part Mock-FOB panels-25 | Alternation/Partial Activity/Repair Request | #REF!
| JACKET |  |  |  | AA06 - Part Mock-GCR-75 | Alternation/Partial Activity/Repair Request | #REF!
| JAMMER |  |  |  | AA07 - Part Mock-One side Leg-50 | Alternation/Partial Activity/Repair Request | #REF!
| JEANS |  |  |  | AA08 - Part Mock-Pocket mock-15 | Alternation/Partial Activity/Repair Request | #REF!
| JEGGINGS |  |  |  | AA09 - Part Mock-Sleeve mock-30 | Alternation/Partial Activity/Repair Request | #REF!
| JOGGERS |  |  |  | AA10 - Part Mock-Thread run-10 | Request Activity/RepairAlternation/Partial | #REF!
| JUMPER |  |  |  | AA11 - Part Mock-Trim look-30 | Alternation/Partial Activity/Repair Request | #REF!
| JUMPSUIT |  |  |  | AA12 - Part Mock-Tube Leg-20 | Alternation/Partial Activity/Repair Request | #REF!
| KHAKIS |  |  |  | AA13 - Part Mock-Waistband-40 | Alternation/Partial Activity/Repair Request | #REF!
| KNEEBAND |  |  |  | AA04 - Part Mock-Zipper-30 | Alternation/Partial Activity/Repair Request | #REF!
| KNIT SET |  |  |  | AD01 - Photoshoot Sample-100 | Review/Marketing/Photoshoot/Advertisement/Catalogue LineBuyer | #REF!
| KURTA |  |  |  | PP01 - Pre-Production (PP) Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| LEGGING |  |  |  | PR22 - Pre-Salesman Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| MITTENS |  |  |  | PR20 - Presentation Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| MUFFLER |  |  |  | PP09 - Production Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| OVERALL |  |  |  | PR01 - Proto Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| OVERCOAT |  |  |  | PP08 - Red Seal Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| PANTS |  |  |  | PP05 - Reference PP Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| PANTY |  |  |  | PR21 - Review Sample-100 | Proto Sample/Concept Sample/Development/Adoption/Presentation/Review Sample | #REF!
| PARKA |  |  |  | MK02 - Rough Body Sample-100 | Internal Mock/Rough Body/Dummy/Trial Fit Sample | #REF!
| POLO |  |  |  | SS01 - Salesman Sample-100 | Salesman Sample | #REF!
| PONCHO |  |  |  | PP06 - Sealer Sample-100 | Pre-Production/Sealer/Production Sample | #REF!
| PULLOVER |  |  |  | TP01 - Shipment Sample-100 | Shipment Sample/Top of Production Sample | #REF!
| PYJAMA |  |  |  | ST01 - Size - Set Sample-100 | Size - Set Sample | #REF!
| ROBE |  |  |  | WS02 - Technique Approval Sample-100 | Wash Sample/Technique Approval Sample | #REF!
| ROBE |  |  |  | TS01 - Testing Sample-100 | TE-GPT/Testing/Wear Test Sample | #REF!
| ROMPER |  |  |  | TP02 - Top of Production (TOP) Sample-100 | Shipment Sample/Top of Production Sample | #REF!
| SARONG |  |  |  | MK04 - Trial Fit Sample-100 | Internal Mock/Rough Body/Dummy/Trial Fit Sample | #REF!
| SASH |  |  |  | WIP1 - WIP Production-100 | WIP Production | #REF!
| SCARF |  |  |  | WS01 - Wash Approval Sample-100 | Wash Sample/Technique Approval Sample | #REF!
| SHAWL |  |  |  | TS03 - Wear Test Sample-100 | TE-GPT/Testing/Wear Test Sample | #REF!
| SHIRT | [5 empty] | #REF!
| SHIRTDRESS | [5 empty] | #REF!
| SHORTS | [5 empty] | #REF!
| SHRUG | [5 empty] | #REF!
| SKIRTS | [5 empty] | #REF!
| SKORTS | [5 empty] | #REF!
| SLIP | [5 empty] | #REF!
| SOCKS | [5 empty] | #REF!
| STOCKINGS | [5 empty] | #REF!
| SUIT | [5 empty] | #REF!
| SWEATER | [5 empty] | #REF!
| SWEATPANT | [5 empty] | #REF!
| SWEATSHIRT | [5 empty] | #REF!
| SWIM SUIT | [5 empty] | #REF!
| THERMAL | [5 empty] | #REF!
| THERMAL | [5 empty] | #REF!
| THONG | [5 empty] | #REF!
| TIE | [5 empty] | #REF!
| TIE SIDE BOTTO | [5 empty] | #REF!
| TOP | [5 empty] | #REF!
| TOP BTM SET | [5 empty] | #REF!
| TRACKSUIT | [5 empty] | #REF!
| TROUSERS | [5 empty] | #REF!
| TSHIRT | [5 empty] | #REF!
| TUNIC | [5 empty] | #REF!
| TURTLE NECK | [5 empty] | #REF!
| UNDERPANTS | [5 empty] | #REF!
| VEIL | [5 empty] | #REF!
| VEST | [5 empty] | #REF!
| VEST | [5 empty] | #REF!
| WAISTCOAT | [5 empty] | #REF!
| WINDCHEATER | [5 empty] | #REF!
| WOVEN KNIT SET | [5 empty] | #REF!
| WOVEN SET | [5 empty] | #REF!
| WRAP | [5 empty] | #REF!
| ZIP JACKET | [5 empty] | #REF!
| ZIP JACKET | [5 empty] | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!